## Project List
S.No | Department Name | Implementing Agency | Name Of The Project | Funding Agency | Project Start Date | Project End Date | Revised Project Start Date | Revised Project End Date | Project Cost | Present Status | Causes Of Delay
1 | Bridges Department, Greater Chennai Corporation | Bridges Department, Greater Chennai Corporation | Construction of integrated ROB in lieu of existing LC No – 2A at Ennore High Road and LC No- 2B at Manali Road in Dn. 38 & 41, Zone – IV | Government - 50% Capital Grant Fund - Rs.10 Cr Railways - 30% | 12.09.2016 |  |  |  | Rs.137.53 Crores
2 | CMWSSB | Chennai Metro Water Supply and Sewerage Board | EngineeringCarrying out Improvement/Modification Works to Existing Sewage Treatment Plants of 110 MLD Capacity at Kodungaiyur, 60 MLD120 MLD Capacity at Koyambedu, 40 MLD54 MLD Capacity at Nesapakkam, 54 MLD60 MLD Capacity at Perungudi with Replacement of existing Mechanical / Electrical / Instrumentation Equipment’sBio Gas Power Production SystemsMinor Civil Repair works at required units for complying with New Discharge Standards specified by CPCB/TNPCBincluding Design, Engineering, BuildCommissioning of additional Technology Processing Units for the capacities of the existing STPs, To comply with the New Discharge Standards specified by CPCB/TNPCB including Operation And Maintenance for Ten Years in Kodungaiyur, Koyambedu, Nesapakkam Perungudi, Chennai | xxxx |  |  |  |  | 222222
3 | CMWSSB | CMWSSB | Providing Comprehensive Water Supply Scheme to Mathur in Chennai City, in Division 19, Zone II | AMRUT-ADB |  |  |  |  | 196
4 | CMWSSB | CMWSSB | Providing Comprehensive Water Supply Scheme to Uthandi in Chennai City in Division 199 Zone XV | AMRUT-ADB |  |  |  |  | 196
5 | CMWSSB | CMWSSB | Providing Comprehensive Underground sewerage Scheme to Manali | AMRUT- ADB | 01.07.2019 | 31.12.2021 |  |  | 60.84 Cr.
6 | CMWSSB | Chennai Metro Water Supply and Sewerage Board | Design\\, Engineering\\, Build and Commissioning of 120 MLD capacity Sewage Treatment Plant in Zone – I at Kodungaiyur with Sequential Batch Reactor (SBR) with Power Generation from Bio-gas including Operation and Maintenance for ten years at Kodungaiyur |  | 05.11.2019 | 04.02.2022 |  |  | Rs.207.49 Crore
7 | CMWSSB | CMWSSB | Providing Comprehensive Water Supply Scheme to Madipakkam in Chennai City, in Division 187 188, Zone XIV | AMRUT-ADB |  |  |  |  | 196
8 | CMWSSB | CMWSSB | Design\\, Build and Operate for 15 years (DBO) a 45 MLD capacity Tertiary Treatment Reverse Osmosis (TTRO) at Kodungaiyur including supply\\, laying DI Transmission mains for conveyance of Product water to various industries in Manali area\\, Chennai | TNSUDP & AMRUT | 21.04.2017 | 20.10.2019 |  |  | 392.61 Crore
9 | CMWSSB | Chennai Metro Water Supply and Sewerage Board | Design, Engineering, BuildCommissioning Sewage Treatment Plant with Sequential Batch Reactor (SBR) with Power Generation from Bio-gas including OperationMaintenance for Ten years - 120MLD capacity at Kodungaiyur Zone – II | Agency |  |  |  |  | 383.85
10 | CMWSSB | Chennai Metro Water Supply and Sewerage Board | Design\\, Build and Commissioning of 60 MLD capacity Sewage Treatment Plant at Perungudi including Operation and Maintenance of the plant for 10 years |  | 15.11.2019 | 14.02.2022 |  |  | Rs.103.71 Crore
11 | CMWSSB | Chennai Metro Water Supply and Sewerage Board | Design\\, Build and Commissioning of 50 MLD capacity Sewage Treatment Plant at Nesapakkam including Operation and Maintenance of the plant for 10 years | AMRUT & TNIPP II | 13.11.2019 | 13.02.2022 |  |  | Rs.85.13 Crore
12 | CMWSSB | CMWSSB | Providing Comprehensive Underground sewerage Scheme to Chinnasekkadu | AMRUT- ADB | 01.07.2019 | 31.12.2021 |  |  | 22.78 Cr.
13 | CMWSSB | CMWSSB | Providing Comprehensive Underground sewerage Scheme to Manapakkam | AMRUT- ADB |  |  |  |  | 241.36
14 | CMWSSB | CMWSSB | Providing Comprehensive Underground sewerage Scheme to Karambakkam | AMRUT- ADB | 01.07.2019 | 31.12.2021 |  |  | 101.81 Cr.
15 | CMWSSB | CMWSSB | Providing Comprehensive Water Supply Scheme to Jalladampettai in Chennai City, in Division 191, Zone XIV | AMRUT-ADB |  |  |  |  | 196
16 | CMWSSB | Chennai Metropolitan Water supply and sewerage Board(CMWSSB) | Design\\, Build and operate for 15 years (DBO) a 45 MLD capacity Tertiary Treatment Reverse Osmosis (TTRO) at Koyambedu including supply\\, laying and maintenance of M.S. transmission main for conveying product water to various industries situated at Irungattukottai\\, Sriperumbudur and Oragadam | AMRUT TNIPP CMCDM CMWSSB Share | 21.04.2017 | 29.11.2019 |  |  | Rs.486.21 Crores
17 | Greater Chennai Corporation | Greater Chennai Corporation | Design, Supply, implement, commission, operate and manage the Command and Control Centre as a part of smart city solutions for Chennai city | Chennai Smart City Limited | 01.07.2019 | One Year implementation and 5 Years Operation and Maintainance |  |  | 149.84 Crore
18 | Highways | Chennai Metropolitan Development Plan wing | Construction of Grade Separator Connecting Medavakkam -Sholinganallur Road junction. Medavakkam Mambakkam road Junction and Mount Medavakkam road junction in Marmalong bridge Irumbuliyur road at Medavakkam | State fund - CMDP Scheme | 08.01.2016 | 11.09.2020 |  |  | 146.41 crores
19 | Highways | Chennai Metropolitan Development Plan wing | Construction of Grade Separator at the Intersection of Taramani Road Tambaram Velachery RoadVelachery Bypass Road at Velachery Vijayanagaram in Chennai City | State fund - CMDP Scheme |  |  |  |  | 100
20 | Highways | Chennai Metropolitan Development Plan wing | Forming six lane of ECR from Km: 11/8-23/2. Thiruvanmiyur to Akkarai (Land Acquisition only) | State fund - CMDP Scheme | - | - |  |  | 778
21 | Highways | Construction & Maintanance | Construction of two tier flyover at five road junction including construction of fly over upto Ramakrishna road junction and four road junction in Salem City. | State Government | 25.02.2016 | 07.06.2019 Ist level (AVR Roundana to Ramakrishna road junction) ; IInd level (Kuranguchavadi to Four road Junction) |  |  | 441
22 | Highways | Chennai Metropolitan Development Plan wing | Formation of link road and construction of bridge across Buckingham canal connecting Rajiv Gandhi and ECR at Neelankkarai. | State fund - CMDP Scheme | - | - |  |  | 204.2
23 | Highways | National Highways | Construction of Vaigai South River Bank Road from Dindigul Road-Theppakulam in Km 0/0 - 6/400 | Govt. of India | 25.02.2019 | 24.08.2020 |  |  | 117 Crores
24 | Highways | METRO wing | Construction of ROB in lieu of LC 32 in between Tambaram and Vandalur Railway Stations near Perungalathur | Government of Tamilnadu and Railways Department 50:50 cost sharing | 24-10-2019 | 23-10-2022 |  |  | 206.83 Crores
25 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | Improvements from Four laning to Six laning of Vandalur – Wallajabad Road (SH-48) km 30/400 – 47/000 including Land Acquisition for formation of Padappai Bye Pass (Phase-IV) | Government fund | 2016-02-26 | 2018-02-25 |  |  | 189.81
26 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | Improvements from four laning to six laning of Vandalur – Wallajabad Road km 47/000-63/800 (SH-48) (Length 16.80 Km ) | Government fund | 2018-04-06 | 2020-04-05 |  |  | 180.09
27 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | Widening the Madurai Ring Road from double lane to four lane from km 0 / 0 – 27 / 2 (BOT - Toll basis) | BOT Toll VGF Rs.80.00 crore | 2017-04-17 | 2019-04-16 |  |  | 213.69
28 | Highways & Minor Ports Departments | ConstructionMaintenance | Construction of Flyover at Goripalayam Junction | Tamilnadu State Government |  |  |  |  | 100
29 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | ldshflhdslhflhdsf | lshsdflhldsf |  |  |  |  | 230 |  | Slow work progress by contractor
30 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | ldshflhdslhflhdsf | lshsdflhldsf |  |  |  |  | 230 |  | Non Satisfaction work & terminating contractor
31 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | skdkhaslkdhlsand | lknsda |  |  |  |  | 340 | pending | Acquisition of land
32 | Highways & Minor Ports Departments | TamilNadu Road Infrastructure Developemtn Corporation | XYZ | XYZ Funding Agency |  |  |  |  | 350 | Pending | Non-Formation Land Acqisition Unit
33 | Highways and Minor Ports | TNRDC | Construction of Two Bypasses at KelambakkamTiruporur along Phase - II of OMR | JICAGoTN | 2018-06-25 | 2021-12-31 |  |  | 243.7
34 | Highways and Minor Ports | TNRDC | Development of Chennai Outer Ring Road Project Phase –II a major Six lane road connectivity from Nemillicheri in NH-205 to Minjur in Thiruvotriyur Ponneri Pancheti (TPP) Road via Padiyanallur in NH-5 for a length of 30.50 Km under Design, Build, Finance, OperateTransfer (DBFOT) on Annuity basis under Public Private Partnership (PPP) on Semi Annual Annuity Basis | DBFOT / GoTN (Project Support Fund Rs.197 Cr.) - Semi Annual Annuity (35 Installments)- Rs.119.97 Cr |  |  |  |  | 4198.95
35 | Highways and Minor Ports | TNRDC | Development of Chennai Outer Ring Road Project Phase – I from Vandalur in NH-45 to Nemilicheri in NH-205 via Nazarathpet in NH-4 for a length of 29.65 Km under Design, Build, Finance, OperateTransfer (DBFOT) on Annuity basis under Public Private Partnership (PPP) on Semi Annual Annuity Basis. | DBFOT / GoTN (Project Support Fund Rs.300 Cr.) Semi Annual Annuity (35 Installments)- Rs.62.13 Cr |  |  |  |  | 864
36 | Highways and Minor Ports | TNRDC | Northern Port Access Road Project - Manali - Minjur -Ponneri belt in Ponneri Taluk (Section - I of Chennai Peripheral Ring Road) | JICAGovt of Tamilnadu |  |  |  |  | 951
37 | Housing & Urban Development Department | M/S. P C Projects (P) Ltd, PC Towers, IInd Floor, 140, Perundurai Road, Erode – 638 011 | Construction of Multi-Storied office Complex Building at Koyambedu, Chennai-92. | Chennai Metropolitan Development Authority | 2016-06-01 | 2018-05-31 |  |  | 105
38 | Housing & Urban Development Department | M/S. P C Projects (P) Ltd, PC Towers, IInd Floor, 140, Perundurai Road, Erode – 638 011 | Construction of New Mofussil Bus Terminus with all infrastructures at Kilambakkam near Vandalur, Kancheepuram District | CMDA's Own Fund | 2019-03-08 | 2021-03-07 |  |  | 393.74
39 | Housing & Urban Development Department | MTP (R) | MRTS Ph- II Extension | GoI / GoTN | 2008-04-01 | 2014-08-28 |  |  | 732.89 |  | Acquisition of land
40 | Housing & Urban Development Department | TNRDC | ORR Phase - II | GoI / GoTN | 2014-08-28 |  |  |  | 1075 |  | Acquisition of land
41 | Industries - TIDCO | TIDCO | Medical Equipment Park | - | Implementation yet to be started | - |  |  | As per revised plan Rs.205 crs (including land cost)
42 | Industries - TIDCO | TIDCO | Polymer Industries Park | Equity by TIDCO - Rs.49.40 Crore Equity by SIPCOT - Rs.49.40 crore Upfront land lease charges to be collected in advance - Rs.78.11 Crore | Implementation yet to be started | - |  |  | Rs.216.91 Crore
43 | Industries - TIDCO | - | Heavy Engineering Hub | Equity:Rs.210 Cr(Proposed) Debt: Rs.491 Cr (Proposed) | Implementation yet to be started | - |  |  | Rs.701 Crore
44 | Industries - TIDCO | TIDEL | CONSTRUCTION OF IT PARK in Pattabiram Village\\, Avadi Taluk\\, Tiruvallur District | Aside Grant of Rs.20 Crs Sanctioned term loan from bank being tied-up | Implementation Yet to be started | 24 Months from start date. |  |  | 235 Crores
45 | Industries - TIDCO | TIDEL | CONSTRUCTION OF ADVANCED COMPUTING & DESIGN ENGINEERING CENTRE (ACDEC) FOR AEROSPACE AND DEFENCE INDUSTRIES in Aerospace Park\\, Vallam ''A''\\, Vadagal Village\\, Sriperumbudur Taluk\\, Kancheepuram District | Aside Grant of Rs.50 Crs Sanctioned term loan from bank being tied-up | ImplementationYet to be started | 24 Months from start date. |  |  | 250 Crores
46 | Industries Department | Tamilnadu Cements Corporation Limited | Cement project | goverment | 2020-03-06 | 2020-03-28 |  |  | 405
47 | Municipal Administration & Water Supply Department | Chennai Metropolitan Water SupplySewerage Board | CWSS to Keeranur | Test |  | 2019-10-31 |  |  | 108
48 | Municipal Administration & Water Supply Department | The Tamil Nadu Water Supply and Drainage Board | p name | fund name |  |  |  |  | 100
49 | SIPCOT | SIPCOT | Setting up of 60 MLD Sea Water Reverse Osmosis Desalination plant in Mullakadu,Thoothukudi District. | TNIFMC | 01.04.2020 (Tentative) | 01.04.2022 (Tentative) |  |  | 634 Crore
50 | Tamil Nadu Trade Promotion Organisation | Tamil Nadu Trade Promotion Organisation | Expansion of Chennai Trade Centre (Phase - II) | TNTPO Fund\\, TIES Grant and Loan from Financial Institutions | April 2020 Tenders floated (third call) | 18 months from the start date |  |  | Rs.254.29 crores plus GST Rs.45.71 crores (18%)